## Sheet 1 - GREENLEAF E-COMMERCE
GREENLEAF E-COMMERCE – RISK DASHBOARD Prepared by: Cameron Naidoo ¦ Date: 23 June 2026 ¦ Classification: Confidential 1. EXECUTIVE RISK SUMMARY GreenLeaf E-Commerce currently has 4 identified risks across its IT and people systems. Of these: 1 is Critical (Score 20) – requiring immediate Board attention. 3 are High (Scores 15–16) – requiring action within 60 days. 0 are Medium/Low – all risks require active treatment. The overall residual risk posture is "Elevated" due to a lack of foundational security controls (MFA, backups, and staff training). No risks are currently being "Accepted" without justification. 2. TOP 3 PRIORITIES FOR THE NEXT 60 DAYS #1 GR-003 - Business Interruption – No tested offsite backups. Ransomware could halt sales for 7+ days. 23/09/2026 - Not Started #2 GR-001 - Unauthorized Access – Admin accounts lack MFA. Credential theft would expose all customer data. 23/07/2026 - In Progress #3 GR-004 - Human Error / BEC – Employees have never received security training. Phishing risk is critical. 23/08/2026 - Not Started 3. KEY METRICS (SNAPSHOT) Total Risks Identified = 4 Inherent Risk Average = 16.8 / 25 Residual Risk Average (after existing controls) = 14.8 / 25 Risks Under Active Mitigation = 1 (GR-001) Risks Needing Budget Approval = 2 (GR-003, GR-004) 4. RECOMMENDED IMMEDIATE ACTIONS Secure CAPEX approval for immutable cloud backup solution (GR-003) – estimated cost: $500/month. Deploy MFA for all admin accounts this week – no cost (free with Microsoft/Google) (GR-001). Procure security awareness training (KnowBe4 or similar) within 14 days (GR-004). Schedule a Quarterly Risk Review meeting with the CTO, CFO, and Head of People to review this register. "This dashboard is a living document. Risk scores will be re-assessed monthly or after any major security incident."
Risk ID | Date | Risk Owner | Asset at Risk | Threat | Vulnerability | Likelihood | Impact | Inherent Score | Existing Controls | Residual Likelihood | Residual Impact | Residual Score | Treatment Decision | Mitigation Plan | Target Date | Status
GR-001 | 23/06/26 | CTO | Customer Credit Card Database | Ransomware / External Hacker | No Multi-Factor Authentication (MFA) on admin accounts. | 4 | 5 | 20 (Critical) | Basic Firewall & Antivirus only. | 3 | 5 | 15 (High) | Mitigate | Enforce MFA on all 5 admin accounts within 30 days. | 23/07/26 | In Progress
GR-002 | 23/06/26 | HR Director | Employee PII (Names, ID, Bank Details) | Insider Threat (Disgruntled ex-employee) | Offboarding process is manual and sometimes delayed. | 3 | 4 | 12 (Medium) | Standard NDA agreements. | 2 | 4 | 8 (Medium) | Mitigate | Automate offboarding to disable access within 1 hour of termination. | 23/08/26 | Not Started
GR-003 | 23/06/26 | CFO | Business Interruption (Web Sales) | Ransomware / System Crash | No offsite backups tested in the last 6 months. | 3 | 5 | 15 (High) | Weekly local backups. | 4 | 5 | 20 (Critical) | Mitigate | Implement immutable cloud backups (AWS S3) with daily testing. | 23/09/26 | Not Started
GR-004 | 23/06/26 | HR | Employee credentials & corporate email system (MS 365/Google Workspace) | Spear-phishing/ business email compromise (BEC) attackers trick employees into revealing passwords or transferring funds | No mandatory annual security awareness training. Employees have never been tested with a simulated phishing campaign | 5 | 4 | 20 (Critical) | Basic Spam filter on email, no user reporting, no training. | 4 | 4 | 16 (High) | Mitigate | 1. Deploy a 30-minute gamified security awareness training module (KnowBe4 or free alternative) for all 50 employees within 60 days. 2. Run a simulated phishing test immediately after training. 3. Implement a "Report Phishing" button in Outlook/Gmail for easy employee reporting. | 2023-08-26 | Not Started
GR-005 | 2023-06-26 | CEO - acts as DPO data protection officer | A) The AWS Cloud Server (The physical/virtual infrastructure storing the data).The Customer Personal Data (The actual PII/Personal Identifiable Information itself).GreenLeaf's Brand Reputation and Trust (If they get fined or exposed, customers will leave). | Complaint, Regulator Fine, Class-Action Lawsuit | No Privacy Policy – customers don't know their rights. No Cookie Banner – the website is illegally tracking EU visitors. No Erasure Process – the company has no workflow to delete data upon request | 4 | 5 | 20 (Critical) | Generic terms of service page - non compliant with GDPR | 5 | 4 | 20 (Critical) | Mitigate | Comprehensive 30-day plan: Hire lawyer for Privacy Policy (Week 1-2), install Cookie Banner immediately (Week 1), document Erasure process (Week 2-3), test everything (Week 4). | 2023-08-26 | Not Started